## Sheet1
ITEM | PRIORITY | NOTES | ADDED | COMPLETED | TESTED
Save libs correctly | 5 | Func object is a delegate and cannot be serialized | 2014-06-06 | 2014-06-08 | 2014-06-19
Check arg num enforced | 4.9 |  | 2014-06-06 | 2014-06-08 | 2014-06-19
Variable tokens for filter | 4.8 | Need way to save methods with variables | 2014-06-06 | 2014-06-08 | 2014-06-19
Finish filter buttons above bottom row | 4.8 |  | 2014-06-08 | 2014-06-19 | 2014-06-19
Make sure new commands/libs are added properly to dropdowns | 4.75 |  | 2014-06-17 | 2014-06-19 | 2014-06-19
Decide whether to replace tuple with obj() | 4.75 |  | 2014-06-21 | 2014-06-24 | 2014-06-24
get Rid of null bugs | 4.73 |  | 2014-06-25 | 2014-06-25 | 2014-06-25
Type enforce filter cmds | 4.7 |  | 2014-06-06 | 2014-06-25 | 2014-06-25
Finish bottom row filter buttons | 4.6 |  | 2014-06-08 | 2014-06-28 | 2014-06-28
Default Folder not working for Import | 4 |  | 2014-06-19 | 2014-06-28 | 2014-06-28
Need button to clear command statement | 4 |  | 2014-06-19 | 2014-06-28 | 2014-06-28
Save state of Multigraph | 4 |  | 2014-06-26 | 2014-07-26 | 2014-07-26
Advanced Statistical Methods | 4 | Look at R, go through excel functions, Tableau | 2014-06-06
Remove all cmdlib, save/load cmds | 4 |  | 2014-02-03
File System Organization | 4 | export tool, folder dropdown | 2014-06-08
Different file types | 4 |  | 2015-01-22
Keep libraries? | 3.01 | No, see below | 2014-06-19 | 2015-01-22 | 2015-01-22
Handle less than expected numArgs | 3 | continue to do | 2014-06-21
Support Numerical Operators | 3 |  | 2014-06-06
Mini-status Windows for Sequential Operations | 3 | Import necessary | 2014-06-06
Make help file | 3 |  | 2014-01-22
Make tooltips | 3 |  | 2014-01-22
Tabbed Browsing/ Better interface structure | 3 | export tool, folder dropdown | 2014-01-22
Default x axis/ string vars | 3 | Add slots for each data point when using one variable | 2014-06-06
Plot multiple vars against one | 3 |  | 2014-06-06
Save plot configs/ plots | 3 | Templates, Long Run: Host plots/graphs | 2014-06-06
Provide example templates | 3 |  | 2014-01-22
Multiple Sets in Filter | 3 | Consider Later | 2014-06-08
Filter Autocomplete parens | 3 |  | 2014-06-19
Allow edits in filter window | 3 |  | 2014-06-27
Speed up import | 3 | How | 2014-06-28
Manual row filtering | 3 |  | 2014-07-26
Fix multiple variable copies in filter dropdown | 3 |  | 2015-01-22
Zoom | 3 | scroll zoom | 2015-01-22
Name csv files that have blanks | 3 |  | 2015-01-22
Use checks or X's instead of squares in varmap | 3 |  | 2015-01-22
Plot button stays grayed (maybe on close and reopen) | 3 | Watch out for this | 2015-01-22
Hotkeys | 2 |  | 2014-06-19
Tab Ordering | 2 |  | 2014-06-19
Make Graphing Look Pretty | 2 | Gridlines, bullet size/shape, etc | 2014-06-06
Dialog locations, properties consistent | 2 | pop up in same place | 2014-06-06
Rename code | 2 | Plot Config/Plot Setup, namelist/setlist | 2014-06-06
Add option controls | 2 | Think about what is needed, Settings in Options window | 2014-06-06
Additional Chart Types | 2 | Visit this before release | 2014-06-06
Filter Autocomplete | 2 | color-code statement | 2014-06-19
Redesign Preview Interface | 2 | mini-status | 2014-06-24
Add variables from more than one set | 2 | Watch out for this | 2014-06-26
Cascading drop down for commands | 2 |  | 2014-06-27
Find better event to trigger filter overwrite than dropdown | 1 | What was this | 2014-06-28
Multidimensional Plots | 1 | Heat Map, Cross Section Slider, etc | 2014-06-06
Dimensional Analysis | 1 |  | 2014-06-06
Scheduling | 1 |  | 2014-06-06